# Effort Estimation Calculator – Project Plan

# Summary

As part of the team plan, this small project builds an internal desktop tool that turns the CI effort estimate matrix into a consistent estimate in a few clicks and shares it in our standard e-mail format. The plan below covers how the team will build it, test it with a small pilot group and roll it out to the CI team.

Developers: Akhilesh Kumar and Ishita Garg

# Objective and scope

The goal is that every CI estimate uses the same matrix, the same formula and the same output format, whoever prepares it.

| In scope (this project) | Out of scope (possible later phase) |
| --- | --- |
| Data & KPIs estimate (CI 1.0 matrix) | Saving estimate history or reports |
| Power BI Dashboard estimate | User login and approval workflow |
| Hours and days at 8 h/day, activity breakdown | Web or mobile version |
| Share form: entity, delivery date, up to 3 CI resources, assumptions | Integration with timesheets or project tools |
| Copy for e-mail and Excel download in the standard 5-column format | Editing the matrix from inside the app |
| Single Windows EXE for the team |  |

# Proposed solution

A small Windows desktop app that applies the estimate matrix automatically and produces the standard e-mail table, so an estimate takes a few selections instead of manual working.

| Feature | How it would work |
| --- | --- |
| Two estimators | Separate tabs for Data & KPIs (CI 1.0 matrix) and Power BI Dashboard |
| Selections | Dropdowns for files, KPIs, pages and sources; buttons for complexity levels |
| Instant result | Total hours, days at 8 h/day, and an activity-wise breakdown |
| Share form | Entity name, delivery date from a calendar, up to 3 CI resources, key assumptions |
| Outputs | Copy the table straight into an Outlook e-mail, or download it as Excel |
| Distribution | One EXE file; team members do not need to install anything |
| Maintenance | All hours and names kept in one settings file, updated by one owner |

Proposed technology: Python with its built-in Tkinter UI library, packaged as a single EXE; no database or server needed.

# Estimate matrix

Each activity's hours = base hours for the chosen level × the volume multiplier; the estimate is the sum of all activities, and days = hours ÷ 8.

Data & KPIs (CI 1.0) — base hours per 10 files or 10 KPIs

| Activity | Level 1 | Level 2 | Level 3 | Multiplier from |
| --- | --- | --- | --- | --- |
| Quality of the Data | Good – 1 h | Average – 2 h | Poor – 3 h | Number of files |
| Level of Data Cleansing | Basic – 2 h | Intermediate – 3 h | Advanced – 4 h | Number of files |
| Data Transformation for Ingestion | Basic – 1 h | Intermediate – 2 h | Advanced – 5 h | Number of files |
| Average complexity of KPIs | Basic – 4 h | Moderate – 8 h | Complex – 12 h | Number of KPIs |

Volume multiplier (files and KPIs): Upto 10 = ×1, 11-20 = ×2, 21-30 = ×3, 31-40 = ×4, 41-50 = ×5. Bands above 10 follow the same per-10 rule and are to be confirmed.

Power BI Dashboard

| Report pages | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| Hours | 3 h | 5 h | 7 h | 9 h | 11 h |

| Activity | Level 1 | Level 2 | Level 3 | Multiplier from |
| --- | --- | --- | --- | --- |
| Data Modelling & Power Query | Basic – 2 h | Intermediate – 4 h | Advanced – 8 h | Data sources, per 5 |
| DAX Measures | Basic – 2 h | Intermediate – 5 h | Advanced – 10 h | Flat for 1-5 pages |
| Visual Design & Layout | Standard – 2 h | Custom – 4 h | Advanced – 6 h | Flat for 1-5 pages |

Data sources multiplier: Upto 5 = ×1, 6-10 = ×2, 11-15 = ×3, 16-20 = ×4. Modelling, DAX and Visual hours are initial values, to be confirmed in Phase 1.

Example: Data & KPIs with 10 files, 10 KPIs, Good / Basic / Basic / Basic = 1 + 2 + 1 + 4 = 8 h = 1 day.

# Plan

The work runs in four phases; each phase starts only when the gate before it is met, so no unverified numbers reach the team.

Phase 1 comes first and mainly needs the confirmed Power BI hours. Durations are not fixed yet and will be proposed once the matrix owner and pilot users are named.